## Risk Assessment
Risk Assessment
Risk ID | Risk | Probability | Consequence | Impact | Risk Factor | Mitigation
|  | 1 - Unlikely |  | 1 - Minor | Impact × Probability
|  | 4 - Very Likely |  | 4 - Significant
1 | Inaccurate model | 3 | Predictions are unreliable | 1 | 3 | Research and try multiple models
2 | Difficulty implementing GUI | 3 | Poor usability or functions inaccessible | 3 | 9 | Help guide for navigating GUI if complex
3 | Loss of work | 1 | Time wasted | 3 | 3 | Use version control and repository hosting
4 | Project requirements change | 1 | Work must be redone/modified | 2 | 2 | Follow an Agile methodology
5 | Data inaccessible | 1 | No data for ML | 4 | 4 | Keep offline version of dataset
6 | Poor performance | 2 | Poor user experience | 2 | 4 | Avoid excess calculations by preprocessing data
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0